## Index
Index of Forms and Charts
FORMS | Description | CHARTS | Description
Launch Meeting/Planning Forms |  | Cumulative Earned Value | Cumulative Planned vs. earned vs. projected earned value
Use these forms to plan a new project |  | Earned Value per Week | Planned, earned, and projected value per week
Project | Project startup and summary form | Cumulative Plan vs. Actual Hours | Cumulative planned vs. actual hours per week
Team | Team member summary | Plan vs. Actual Hours per Week | Planned vs. actual hours per week
Roles | TSPe role assignments | Percent Defect Free | Percent of components that are defect free by phase
Goals | Team goals | Cumulative Defects Removed by Phase | Cumulative defects removed by phase for each component
SUMS | Size summary | Defects Removed by Phase | Defects removed by phase for each component
Task | Task plan template | Defect Density by Phase | Defects per KLOC by phase for each component
Schedule | Schedule plan template | Review Rates | Inspection and review rates for each component
|  | Phase Yield | Phase yield for each component
|  | Process Yield | Process yield for each component
|  | Quality Profile | Five point quality profile for each component
|  | Time in Phase% | Percentage of time spent in each phase
|  | Defects Injected% | Percentage of defects injected in each phase
|  | Defects Removed% | Percentage of defects removed in each phase
Weekly Meeting/Tracking Forms
Use these forms for gathering data and tracking
TimeLog | Time recording Log
DefectLog | Defect recording log
Weekly meeting status report
Task | Task plan template
Schedule | Schedule plan template
Quality actuals for system and components
Resource actuals for system and components
Defects injected/removed for system and components
Standards
Phases | TSPe process phase standard
DefectTypes | Defect type standard

## TSPi Instructions
TSPi Support Tool Instructions
Strategy Development and Planning
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Before STRAT1 | Team Leader | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Before STRAT1 | Team Leader | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Before STRAT1 | Team Leader | Enter the role assignments on the Roles worksheet. | Roles!B2
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
STRAT1: Produce the Size Estimate | Planning Manager | Enter on the SUMS worksheet, the names and size estimates of all assemblies and parts for this cycle. | SUMS!B8
PLAN1: Produce the Task Plan | Planning Manager | Click the Generate Task List button to create a default task list. | Task!A8
PLAN1: Produce the Task Plan | Planning Manager | Revise the task list adding or deleting tasks as necessary. Then for each task, estimate the size where appropriate, the time, and the time for each engineer assigned to the task. | Task!A8
PLAN1: Produce the Schedule Plan | Planning Manager | Enter hours per week in the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
| Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate a schedule. | Task!A8
PLAN1: Quality Plan | Team | Before creating the quality plan, review the quality standard in the textbook.
PLAN1: Quality Plan | Quality/Process Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
PLAN1: Quality Plan | Quality/Process Manager | Enter estimated phase yields for each phase. | SUMQ!D55
PLAN1: Quality Plan | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
PLAN: Balance Workload | Planning Manager | Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the copies automatically. | Team!B2
PLAN: Balance Workload | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set their planned hours to zero). | Task!A8
PLAN: Balance Workload | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
PLAN: Balance Workload | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
PLAN: Balance Workload | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Weekly Tracking
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
STRAT, PLAN, REQ, DES, IMP, TEST, PM | All team members | During all TSPi phases, use the time log to record data on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
REQ, DES, IMP, TEST | All team members | During TSPi phases REQ, DES, IMP, and TEST, use the defect log to record data on each defect. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
Weekly | All team members | Click the Update Project button on the Project worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!C8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A2
Weekly | Planning Manager | Select the Project worksheet and click the update project button before printing status reports for the weekly meeting. | Project!Name
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!C8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Cycle Postmortem
TSPi Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the cycle. | Project!Name

## TSP Instructions
TSPi Support Tool Instructions
Strategy Development and Planning
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
Launch Meeting 2 | Launch Coach or Planning Manager | Fill out the project information on the Project worksheet (Name, Team name, Project name, Start Date, Instructor, Cycle). | Project!Name
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team member names, initials, phone numbers, e-mail addresses, and filenames for the team members workbooks in the Team worksheet. | Team!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the role assignments on the Roles worksheet. (Optional) | Roles!B2
Launch Meeting 2 | Launch Coach or Planning Manager | Enter the team goals on the Goals worksheet. (Optional) | Goals!A3
STRAT: Establish Team Goals | Planning Manager | Enter the team goals on the Goals worksheet | Goals!B3
Launch Meeting 3 | Launch Coach or Planning Manager | Enter all the software assemblies identified during this meeting. Enter the name, assembly/part flag, part of, and size measure. Requirements and High-Level Design documents may also be entered on SUMS. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter on the SUMS worksheet, the size estimates of all software assemblies. | SUMS!B8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Generate Task List button to create an initial task list based on the assemblies on SUMS. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Revise the initial task list by adding or deleting tasks as necessary. Then complete the estimate for each task by entering a size estimate, size measure, rate in units per hour, the estimated hours, and the number of engineers assigned to the task. | Task!A8
Launch Meeting 4 | Launch Coach or Planning Manager | Enter hours per week for the team on the Schedule template. Hours per week are based on the total hours for the team for each week in the schedule. | Schedule!C8
Launch Meeting 4 | Launch Coach or Planning Manager | Click the Update Task and Schedule Plan button on the Task Worksheet to generate the overall plan. | Task!A8
Launch Meeting 5 | Team | Before creating the quality plan, review the quality guidelines in the TSP Launch Notebook
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter the planned defect injection rates for each phase on the SUMQ worksheet. | SUMQ!D82
Launch Meeting 5 | Launch Coach, Planning Manager, or Quality Manager | Enter estimated phase yields for each phase. | SUMQ!D55
Launch Meeting 5 | Team | Review the calculated defect removal rates and defect densities (Defects/KLOC) against the Quality Standard. If necessary, adjust planned time (Task worksheet), defect injection rates (SUMQ), or defect removal yields (SUMQ).
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member(s) assigned to each task in the resources column on worksheet Task. | Task!A8
Launch Meeting 6 | Launch Coach or Planning Manager | Enter the initials of the team member that owns each leaf assembly in the owner column on worksheet SUMS. Note that plan and actual size are copied from the owner's workbook to the team workbook during consolidation, so each leaf assembly MUST have an owner. | SUMS!B8
Launch Meeting 6 | Launch Coach or Planning Manager | Make 1 copy of the team workbook for the consolidated team plan. Make 1 copy of the team workbook for each engineer. Use the filename entered on the Team worksheet (Workbook Filename). Click the Make copies... button to create the engineer's copies automatically. | Team!B2
Launch Meeting 6 | Each engineer | Revise the tasks in the Task worksheet to reflect the individual engineers workload (e.g. delete task not assigned to you, and where you share an assignment with other engineers, set the column Number of Engineers to 1). | Task!A8
Launch Meeting 6 | Each engineer | Revise the schedule plan on the Schedule worksheet to reflect your available hours per week. | Schedule!C8
Launch Meeting 6 | Each engineer | Click the Update Task and Schedule Plan button on the Task Worksheet to generate your individual plan. Repeat the previous two steps until you are satisfied with the plan
Launch Meeting 6 | Planning Manager | Load the engineers' individual worksheets and the consolidated team plan workbook into the same folder. Open the consolidated team plan workbook. Click the consolidate plan button on the Team worksheet to build a consolidated plan | Team!B2
Launch Meeting 6 | All team members | If necessary, reassign tasks to balance the workload and repeat the previous 3 steps until a balanced plan is achieved. If planned times for any task change, review the quality plan and revise it if necessary.
Launch Meeting 7 | Launch Coach or Planning Manager | Enter the team risks on the IRTL worksheet. (Optional) | IRTL!B7
Weekly Tracking
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
All | All team members | While working, use the time log to record time spent on each task. Include the assembly and phase for each task, the date, start time, interrupt time, stop time, and comments. | LOGT!A7
All | All team members | While working, use the defect log to record each defect found. Include the date, number, type, assembly, phase injected, phase removed, fix time, fix reference, and description | LOGD!A7
All | All team members | While working, use the issue/risk tracking log (IRTL) to record new issues and risks or to change status of existing issues or risks. | IRTL!B7
All | All team members | To review status against your plan click the Update Project button on the project worksheet. | Project!B3
Weekly | All team members | Ensure that the completion data for all completed tasks has been entered, and all size, time, and defect data for the week have been entered.
Weekly | All team members | Review the task on worksheet Task and move all organize them into the following order. 1-completed tasks 2-tasks planned for the next two weeks 3-remaining tasks | Task!A8
Weekly | All team members | Click the Update Project button on the Project worksheet to update individual plans. Print the Task and Schedule worksheets. | Project!Name
Weekly | All team members | Print the Task worksheet. | Task!A8
Weekly | All team members | Print the Schedule worksheet. | Schedule!A8
Weekly | All team members | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | All team members | Send a copy of your workbook to the planning manager for use in preparing the team's consolidated weekly report.
Weekly | Planning Manager | Update consolidated team plan with the current week's data and prepare status reports for the weekly meeting.
Weekly | Planning Manager | Load the individual engineers workbooks and the consolidated team workbook into the same folder. Open the consolidated team workbook. Click the Consolidate Plans button on Team worksheet to update consolidated team plan with the current week's data. | Team!A3
Weekly | Planning Manager | Print the Task worksheet. | Task!A8
Weekly | Planning Manager | Print the Schedule worksheet. | Schedule!A8
Weekly | Planning Manager | Prepare a Week report. The worksheet Week includes the planning summary information required for the week report. | Week!C2
Weekly | Planning Manager | Prepare a weekly issue/risk report. The worksheet IRWeek contains the information for this reportt. | IRWeek!C2
Weekly | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Earned Value -Plan vs. Actual Hours | Project!Name
Weekly during implementation and testing phases | Planning Manager | Select the Project worksheet, select the assembly SYSTEM, then select and print the following charts: -Defect Removal Profile -Quality Profile -Percent Defect Free | Project!Name
Project and Phase Postmortem
TSP Process : Step | WHO | TOOL INSTRUCTIONS | FORM
PM | All team members | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | All team members | Select the Project worksheet and click the export button to save a copy of your data for the cycle. | Project!Name
PM | Planning Manager | Follow the weekly tracking instructions to prepare and print copies of the final task, schedule, and week reports. | See weekly tracking instructions
PM | Planning Manager | Select the SUMP worksheet and print a SUMP form for the SYSTEM and each assembly | SUMP!B2
PM | Planning Manager | Select the SUMQ worksheet and print a SUMQ form for the SYSTEM and each assembly | SUMQ!B2
PM | Planning Manager | Select the SUMS worksheet and print a SUMS form | SUMS!B8
PM | Planning Manager | Select the IRTL worksheet and print a copy of all team issues and risk | IRTL!B7
PM | Planning Manager | Select the Project worksheet and click the export button to save a copy of the consolidated team data for the phase or project. | Project!Name

## PlanGuide
General | - If your team does not have historical data, use these guidelines as standard planning factors. - In all cases, use your judgement. If some guideline does not fit your case, use your best estimate instead.
TSP Plans | Overall plan - produced first by the total team and later adjusted to conform to the balanced plan. Bottom-up plan - produced by each engineer for the next phase Balanced plan - the next phase plan after load balancing
Requirements | - The Requirements process depends heavily on The nature of The project, so no General guidelines are given. - In General, expect that all input materials will have be to inspected and substantially reworked.
Requirements Inspections | - The QUAL guideline provides a General factor to use In determining The time needed for The Requirements inspection. - Again, If this number is unrealistic for your project and situation, use your best estimate.
High-Level Design | - The High-Level Design process is highly variable and The time depends principally on The size, complexity, and General nature of The system, so no General guideline is given. - Without prior data, most teams substantially underestimate The time High-Level Design will require.
Implementation Phase | Implementation covers detailed design through unit test. - Calculate total implementation time from LOC/hour rates. - New or large modifications: about 10 LOC per hour. - Small changes to large systems: about 5 LOC per hour. - Pick a number that seems appropriate for your project. - Maintenance fixes, use an average rate: 5 and 20 hours per fix, depending on complexity and degree of testing.
Implementation Allocation | In estimating the implementation phases, - Make an overall estimate based on LOC/hour rates. - Then use these percentages to Calculate The phase times.
Detailed design - 22.1%
Detailed design review - 11.1%
Detailed design inspection - 8.8%
Coding - 20.0%
Code review - 10.0%
Compiling - 3.4%
Code inspection - 8.8%
Unit test - 15.8%
Integration and System Test | For these phases, estimate the defect-free test time and add 5 hours per defect in integration and 10 hours in system test

## QualGuide
Measure | Goal | Comments
Percent Defect Free (PDF)
Compile | > 10%
Unit Test | > 50%
Integration Test | > 70%
System Test | > 90%
Defects/KLOC:
Total defects injected | 75 - 150 | If not PSP trained, use 100 to 200.
Compile | < 10 | All defects
Unit Test | < 5 | All major defects (in source LOC)
Integration Test | < 0.5 | All major defects (in source LOC)
System Test | < 0.2 | All major defects (in source LOC)
Defect Ratios
Detailed design review defects /unit test defects | > 2.0 | All major defects (in source LOC)
Code review defects/compile defects | > 2.0 | All major defects (in source LOC)
Development Time Ratios
Requirements inspection/requirements time | > 0.25 | Elicitation in requirements time
High-level design inspection/high-level design time | > 0.5 | Design work only, not studies
Detailed design/coding time | > 1.00
Detailed design review/detailed design time | > 0.5
Code review/code time | > 0.5
Review and Inspection Rates
Requirements pages/hour | < 2 | Single-spaced text pages
High-level design pages/hour | < 5 | Formatted design logic
Detailed design text lines/hour | < 100 | Pseudocode ~ equal to 3 LOC
Code LOC/hour | < 200 | Logical LOC
Defect Injection and Removal Rates
Requirements defects injected/hour | 0.25 | Only major defects
Requirements inspection defects removed/hour | 0.5 | Only major defects
High-level design defects injected/hour | 0.25 | Only major defects
High-level design inspection defects removed/hour | 0.5 | Only major defects
Detailed design defects injected/hour | 0.75 | Only design defects
Detailed design review defects removed/hour | 1.5 | Only design defects
Detailed design inspection defects removed/hour | 0.5 | Only design defects
Code defects injected/hour | 2 | All defects
Code review defects removed/hour | 4 | All defects in source LOC
Compile defects injected/hour | 0.3 | Any defects
Code inspection defects removed/hour | 1 | All defects in source LOC
Unit test defects injected/hour | 0.067 | Any defects
Phase Yields
Team requirements inspections | ~ 70% | Not counting editorial comments
Design reviews and inspections | ~ 70% | Using state analysis, trace tables
Code reviews and inspections | ~ 70% | Using personal checklists
Compiling | ~ 50% | 90+ % of syntax defects
Unit test - at 5 or less defects/KLOC | ~ 90% | For high defects/KLOC - 50-75%
Integration and system test - at < 1.0 defects/KLOC | ~ 80% | For high defects/KLOC - 30-65%
Acceptance test - at < 1.0 defects/KLOC | ~ 65% | For high defects/KLOC - 30%
Before compile | >75% | Assuming sound design methods
Before unit test | > 85% | Assuming logic checks in reviews
Before integration test | > 97.5% | For small products, 1 defect max.
Before system test | > 99% | For small products, 1 defect max.

## Project
TSPi | - Project Summary | [5 empty] | Plan | Actual | Phase | %
[6 empty] | Design/Code Time | 0 | 0 | Management and Miscellaneous
Name | Catálogo de Productos de Belleza Be Beautiful | Date | 2026-06-23 |  |  | Code Review Time | 0 | 0 | Launch and Strategy
Project | Desarrollo de Software en Equipo | Start Date | 2026-05-13 |  |  | Compile Defects/KLOC | 1 | 1 | Planning
Team | Subgrupo 4 | Instructor | Martinez, Natalia | 4 | 8 | Unit Test Ddefects/KLOC | 1 | 1 | Requirements
Assembly |  | Cycle |  |  |  | Design Review Time | 0 | 0 | System Test Plan
Version: | TSPi.20041202. ©2004 Addison Wesley . | Today's Date Override |  |  |  | COMPILE | 3.4722 |  | REQ Inspection
[6 empty] | CODEINSP | 2.7778 |  | High-Level Design
[6 empty] | UT | 2.0833 |  | Integration Test Plan
[6 empty] | IT | 0 |  | HLD Inspection
[6 empty] | ST | 0 |  | Detailed Design
[6 empty] | 1 Year | 0 |  | DLD Review
[6 empty] | Product Life | 0 |  | Test Development
[6 empty] | QPI | 0 | 0 | DLD Inspection
Code
Code Review
Compile
Code Inspection
Unit Test
Build and Integration Test
System Test
Documentation
Postmortem

## Team
ID | Name | Initials | Phone | e-mail | Workbook Filename | Planned Tasks | Planned Task Hours | Planned Schedule Weeks
1 | Lozano Beltrán Andrea | LBA | 3104448568 | alozanob@poligran.edu.co | LBA | 5 | 9.2 | 4
2 | Luis Sánchez Edison Norvey | ENLS | 3155197502 | enluis@poligran.edu.co | ENLS | 5 | 23.2 | 4
3 | Mesa Molina Camilo | MMC | 3239390438 | cmesammo@poligran.edu.co | MMC | 7 | 33.2 | 4
4 | Lugo Polo Cindy Catherine | LPCC | 3156285835 | ccalugop@poligran.edu.co | LPCC | 4 | 16.8 | 4
5 | Jiménez Betancourt Ángel Damian | JBAD | 3134141803 | adajimenez@poligran.edu.co | JBAD | 3 | 3.7 | 4
6 | Montañez Ruiz Miguel | MRM | 3208641721 | manmontanez@poligran.edu.co | MRM | 5 | 7 | 4
[6 empty] | 29 | 93.1 | 4

## Goals
|  | Measures |  | Tracking
Stakeholders | Goal | Goal | Actual | Who | When
Equipo Be Beautiful | Mantener desviación de esfuerzo controlada | ≤ 15% | 4,73% | Edison | Cierre 23/06/2026
Equipo Be Beautiful | Cerrar defectos críticos | 0 abiertos | 0 abiertos | Cindy | Semana 5
Equipo Be Beautiful | Remoción temprana de defectos | ≥ 80% | 87,50% | Cindy | Semana 5
Equipo Be Beautiful | Cobertura de requisitos | 100% | 100% | Cindy / Miguel | Semana 5
Docente / rúbrica | Consolidar evidencia TSP | LOGT, LOGD, WEEK, TASK, SUMS | Actualizado | Edison / equipo | Entrega 3
Equipo Be Beautiful | Mantener alcance realista del prototipo | Sin backend real / sin pagos reales | Controlado | Andrea / Camilo | Semana 5

## Roles
Team Member Roles |  | Design | Implementation | Integration and Test
Team Leader | LBA
Development Manager | MMC
Planning Manager | ENLS
Quality/Process Manager | LPCC
Support Manager | JBAD
Developer / Tester de apoyo | MRM
Quality Manager | LPCC
Support Manager | JBAD
Test Manager | MRM
Developer / Tester de apoyo | MRM

## SUMP
TSPi Plan Summary - Form SUMP
Name | Catálogo de Productos de Belleza Be Beautiful |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  | Instructor | Martinez, Natalia
Assembly |  |  |  | Cycle | Entrega 3
Program Size | Plan | Actual
Total Requirements Pages (SRS) | 0 | 0
Total HLD Pages (SDS)
Total Detailed Design Lines
Base LOC (B)
Deleted LOC (D)
Modified LOC (M)
Added LOC (A) | 1091 | 1091
Reused LOC (R)
New and Changed LOC (N) | 1091 | 1091
Total LOC (T) | 1091 | 1091
Total New Reuse LOC
Estimated Object LOC (E) | 1091 | 1091
Upper Prediction Interval (70%)
Lower Prediction Interval (70%)
Time in Phase (hours) | Plan | Actual | Actual%
Management and Miscellaneous | 10 | 10.7 | 0.10974
Launch and Strategy | 0 | 0 | 0
Planning | 8 | 8.4 | 0.086154
Requirements | 0 | 0 | 0
System Test Plan | 0 | 0 | 0
REQ Inspection | 0 | 0 | 0
High-Level Design | 14 | 14.8 | 0.15179
Integration Test Plan | 0 | 0 | 0
HLD Inspection | 0 | 0 | 0
Detailed Design | 0 | 0 | 0
DLD Review | 0 | 0 | 0
Test Development | 0 | 0 | 0
DLD Inspection | 0 | 0 | 0
Code | 28 | 29.4 | 0.30154
Code Review | 0 | 0 | 0
Compile | 0 | 0 | 0
Code Inspection | 0 | 0 | 0
Unit Test | 0 | 0 | 0
Build and Integration Test | 0 | 0 | 0
System Test | 20 | 21.1 | 0.21641
Documentation | 13.1 | 13.1 | 0.13436
Postmortem | 0 | 0 | 0
Total | 93.1 | 97.5 | 1
Total Time UPI (70%)
Total Time LPI (70%)
Defects Injected | Plan | Actual | Actual%
Planning | 8 | 8 | 50%
Requirements | 3 | 3 | 18.75%
System Test Plan | 1 | 1 | 6.25%
REQ Inspection | 0 | 0 | 0%
High-Level Design | 0 | 0 | 0%
Integration Test Plan | 0 | 0 | 0%
HLD Inspection | 0 | 0 | 0%
Detailed Design | 0 | 0 | 0%
DLD Review | 0 | 0 | 0%
Test Development | 0 | 0 | 0%
DLD Inspection | 0 | 0 | 0%
Code | 4 | 4 | 25%
Code Review | 0 | 0 | 0%
Compile | 0 | 0 | 0%
Code Inspection | 0 | 0 | 0%
Unit Test | 0 | 0 | 0%
Build and Integration Test | 0 | 0 | 0%
System Test | 0 | 0 | 0%
Total Development Defects Injected | 16 | 16 | 100%
Defects Removed | Plan | Actual | Actual% |  |  | Phase | Plan | Actual
Planning | 10 | 10 | 71.43% |  |  | Planning | 10 | 10
Requirements | 0 | 0 | 0% |  |  | Requirements | 10 | 10
System Test Plan | 0 | 0 | 0% |  |  | System Test Plan | 10 | 10
REQ Inspection | 0 | 0 | 0% |  |  | REQ Inspection | 10 | 10
High-Level Design | 0 | 0 | 0% |  |  | High-Level Design | 10 | 10
Integration Test Plan | 0 | 0 | 0% |  |  | Integration Test Plan | 10 | 10
HLD Inspection | 0 | 0 | 0% |  |  | HLD Inspection | 10 | 10
Detailed Design | 0 | 0 | 0% |  |  | Detailed Design | 10 | 10
DLD Review | 0 | 0 | 0% |  |  | DLD Review | 10 | 10
Test Development | 0 | 0 | 0% |  |  | Test Development | 10 | 10
DLD Inspection | 0 | 0 | 0% |  |  | DLD Inspection | 10 | 10
Code | 4 | 4 | 28.57% |  |  | Code | 14 | 14
Code Review | 0 | 0 | 0% |  |  | Code Review | 14 | 14
Compile | 0 | 0 | 0% |  |  | Compile | 14 | 14
Code Inspection | 0 | 0 | 0% |  |  | Code Inspection | 14 | 14
Unit Test | 0 | 0 | 0% |  |  | Unit Test | 14 | 14
Build and Integration Test | 0 | 0 | 0% |  |  | Build and Integration Test | 14 | 14
System Test | 0 | 0 | 0% |  |  | System Test | 14 | 14
Total Development Defects Removed | 14 | 14 |  |  |  | Acceptance Test | 14 | 14
Acceptance Test | 0 | 0 |  |  |  | Product Life | 14 | 14
Product Life | 0 | 0
Summary | Plan | Actual
LOC/Hour | 11.7186 | 11.1897
CPI (Cost-Performance Index) |  | 0.95487
% Reuse | 0% | 0%
% New Reuse | 0% | 0%

## SUMQ
TSPi Quality Plan - Form SUMQ
Name | Catálogo de Productos de Belleza Be Beautiful |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  | Instructor | Martinez, Natalia
Assembly |  |  |  | Cycle | Entrega 3
SYSTEM Percent Defect Free |  |  | Actual
In Compile |  |  | 0%
In Unit Test |  |  | 0%
In Build and Integration Test |  |  | 0%
In System Test |  |  | 0%
In Acceptance Test |  |  | 0%
In Product Life |  |  | 0%
Defects/Page |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
Defects/KLOC |  | Plan | Actual
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0 | 0
Unit Test |  | 0 | 0
Build and Integration Test |  | 0 | 0
System Test |  | 0 | 0
Total Development |  | 14.55 | 14.55
Acceptance Test |  | 0 | 0
Product Life |  | 0 | 0
Total |  | 14.55 | 14.55
Defect Ratios |  | Plan | Actual
DLD Review/Unit Test |  | 0 | 0
Code Review/Compile |  | 0 | 0
Development Time Ratios |  | Plan | Actual
REQ Inspection/Requirements |  | 0 | 0
HLD Inspection/High-Level Design |  | 0 | 0
Detailed Design/Code |  | 0 | 0
DLD Review/Detailed Design |  | 0 | 0
Code Review/Code |  | 0 | 0
Inspection/Review Rates |  | Plan | Actual
REQ Inspection |  | 0 | 0
HLD Inspection |  | 0 | 0
DLD Review |  | 0 | 0
DLD Inspection |  | 0 | 0
Code Review |  | 0 | 0
Code Inspection |  | 0 | 0
A/FR |  | 0 | 0.164
Phase Yields |  | Plan | Actual |  |  | Phase Yield Planning Guidelines
Planning |  |  | 125% |  |  | Planning | 0%
Requirements |  |  | 0% |  |  | Requirements | 0%
System Test Plan |  |  | 0% |  |  | System Test Plan | 0%
REQ Inspection |  |  | 0% |  |  | REQ Inspection | 70% | Not counting editorial comments
High-Level Design |  |  | 0% |  |  | High-Level Design | 0%
Integration Test Plan |  |  | 0% |  |  | Integration Test Plan | 0%
HLD Inspection |  |  | 0% |  |  | HLD Inspection | 70% | Using state analysis, trace tables
Detailed Design |  |  | 0% |  |  | Detailed Design | 0%
DLD Review |  |  | 0% |  |  | DLD Review | 70% | Using state analysis, trace tables
Test Development |  |  | 0% |  |  | Test Development | 0%
DLD Inspection |  |  | 0% |  |  | DLD Inspection | 70% | Using state analysis, trace tables
Code |  |  | 66.67% |  |  | Code | 0%
Code Review |  |  | 0% |  |  | Code Review | 70% | Using personal checklists
Compile |  |  | 0% |  |  | Compile | 50% | 90+ % of syntax defects
Code Inspection |  |  | 0% |  |  | Code Inspection | 70%
Unit Test |  |  | 0% |  |  | Unit test - at < 5 defects/KLOC | 90% | For high defects/KLOC - 50-75%
Build and Integration Test |  |  | 0% |  |  | Integration test at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
System Test |  |  | 0% |  |  | System test - at < 1.0 defects/KLOC | 80% | For high defects/KLOC - 30-65%
Acceptance Test |  |  | 0% |  |  | Acceptance test - at < 1.0 defects/KLOC | 65% | For high defects/KLOC - 30%
Process Yields |  | Plan | Actual
% Before Compile |  | 87.5% | 8750%
% Before Unit Test |  | 87.5% | 8750%
% Before Build and Integration Test |  | 87.5% | 8750%
% Before System Test |  | 87.5% | 8750%
% Before Acceptance Test |  | 87.5% | 8750%
Defect Injection Rates (Defects Injected Per Hour) |  | Plan | Actual |  |  | Defect Injection Rates Planning Guidelines
Planning |  |  | 0.95238 |  |  | Planning | 0
Requirements |  |  | 0 |  |  | Requirements | 0.25 | Only major defects
System Test Plan |  |  | 0 |  |  | System Test Plan | 0
REQ Inspection |  |  | 0 |  |  | REQ Inspection | 0
High-Level Design |  |  | 0 |  |  | High-Level Design | 0.25 | Only major defects
Integration Test Plan |  |  | 0 |  |  | Integration Test Plan | 0
HLD Inspection |  |  | 0 |  |  | HLD Inspection | 0
Detailed Design |  |  | 0 |  |  | Detailed Design | 0.75 | Only design defects
DLD Review |  |  | 0 |  |  | DLD Review | 0
Test Development |  |  | 0 |  |  | Test Development | 0
DLD Inspection |  |  | 0 |  |  | DLD Inspection | 0
Code |  |  | 0.13605 |  |  | Code | 2 | All defects
Code Review |  |  | 0 |  |  | Code Review | 0
Compile |  |  | 0 |  |  | Compile | 0.3 | Any defects
Code Inspection |  |  | 0 |  |  | Code Inspection | 0
Unit Test |  |  | 0 |  |  | Unit Test | 0.067 | Any defects
Build and Integration Test |  |  | 0 |  |  | Build and Integration Test | 0
System Test |  |  | 0 |  |  | System Test | 0
Defect Removal Rates |  | Plan | Actual
Planning |  | 1.25 | 1.1905
Requirements |  | 0 | 0
System Test Plan |  | 0 | 0
REQ Inspection |  | 0 | 0
High-Level Design |  | 0 | 0
Integration Test Plan |  | 0 | 0
HLD Inspection |  | 0 | 0
Detailed Design |  | 0 | 0
DLD Review |  | 0 | 0
Test Development |  | 0 | 0
DLD Inspection |  | 0 | 0
Code |  | 0.14286 | 0.13605
Code Review |  | 0 | 0
Compile |  | 0 | 0
Code Inspection |  | 0 | 0
Unit Test |  | 0 | 0
Build and Integration Test |  | 0 | 0
System Test |  | 0 | 0

## SUMS
TSPi Size Summary - Form SUMS
| Name | Catálogo de Productos de Belleza Be Beautiful
| Team | Subgrupo 4
| Date | 2026-06-23
| Instructor | Martinez, Natalia
| Cycle | Entrega 3 |  |  |  | Planned Size | [7 empty] | Actual Size | [7 empty] | Planned Defects Injected | [19 empty] | Actual Defects Injected | [19 empty] | Planned Defects Removed | [19 empty] | Actual Defects Removed | [19 empty] | Planned Time | [21 empty] | Actual Time
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours
T01 | Correcciones de Entrega 1 y ajustes del nombre Be Beautiful | P | Be Beautiful | Andrea | LOC proxy | 0 | 0 | 0 | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 36 | 0 | 36 | 36 | 0
T02 | Repositorio, estructura de carpetas y ambiente local | P | Be Beautiful | Ángel | LOC proxy | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0
T03 | Módulo de autenticación: registro, login y sesión local | P | Be Beautiful | Edison / Camilo | LOC proxy | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 0 | 0 | 0 | 0 | 64 | 0 | 64 | 64 | 0
T04 | Catálogo seed de 20 productos | P | Be Beautiful | Edison / Miguel | LOC proxy | 0 | 0 | 0 | 96 | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 96 | 0 | 96 | 96 | 0
T05 | Interfaz de catálogo, tarjetas y filtros visuales | P | Be Beautiful | Andrea / Camilo | LOC proxy | 0 | 0 | 0 | 65 | 0 | 65 | 65 | 0 | 0 | 0 | 0 | 65 | 0 | 65 | 65 | 0
T06 | Vista de detalle de producto | P | Be Beautiful | Camilo | LOC proxy | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 16 | 16 | 0
T07 | Búsqueda básica y búsqueda avanzada | P | Be Beautiful | Camilo / Miguel | LOC proxy | 0 | 0 | 0 | 116 | 0 | 116 | 116 | 0 | 0 | 0 | 0 | 116 | 0 | 116 | 116 | 0
T08 | Carrito de compras: agregar, actualizar y eliminar productos | P | Be Beautiful | Camilo / Edison | LOC proxy | 0 | 0 | 0 | 93 | 0 | 93 | 93 | 0 | 0 | 0 | 0 | 93 | 0 | 93 | 93 | 0
T09 | Validación de stock, subtotales y total general | P | Be Beautiful | Edison / Camilo | LOC proxy | 0 | 0 | 0 | 45 | 0 | 45 | 45 | 0 | 0 | 0 | 0 | 45 | 0 | 45 | 45 | 0
T10 | Confirmación simulada de pedido | P | Be Beautiful | Andrea / Miguel | LOC proxy | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0
T11 | Mensajes del sistema y textos de interfaz | P | Be Beautiful | Cindy / Andrea | LOC proxy | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 40 | 0 | 40 | 40 | 0
T12 | Matriz de pruebas y ejecución funcional | P | Be Beautiful | Cindy / Miguel | LOC proxy | 0 | 0 | 0 | 85 | 0 | 85 | 85 | 0 | 0 | 0 | 0 | 85 | 0 | 85 | 85 | 0
T13 | Corrección de defectos e integración del prototipo | P | Be Beautiful | Todo el equipo | LOC proxy | 0 | 0 | 0 | 66 | 0 | 66 | 66 | 0 | 0 | 0 | 0 | 66 | 0 | 66 | 66 | 0
T14 | Workbook TSP, LOGT, LOGD, SUMS y reportes semanales | P | Be Beautiful | Edison | LOC proxy | 0 | 0 | 0 | 146 | 0 | 146 | 146 | 0 | 0 | 0 | 0 | 146 | 0 | 146 | 146 | 0
T15 | Actas, plan de calidad, riesgos y consolidado documental | P | Be Beautiful | Andrea / Cindy / equipo | LOC proxy | 0 | 0 | 0 | 171 | 0 | 171 | 171 | 0 | 0 | 0 | 0 | 171 | 0 | 171 | 171 | 0
T16 | Evidencias, respaldo, repositorio y soporte de entrega | P | Be Beautiful | Ángel / Miguel | LOC proxy | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 20 | 0 | 20 | 20 | 0

## S
ID | Assembly, Sub-Assembly, or Part Name | (A)ssembly or (P)art | Parent Assembly Name | Owner | Size Measure | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Base | Deleted | Modified | Added | Reused | New and Changed | Total | Total New Reuse | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Acceptance Test | Product Life | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Management and Miscellaneous | Launch and Strategy | Planning | Requirements | System Test Plan | REQ Inspection | High-Level Design | Integration Test Plan | HLD Inspection | Detailed Design | DLD Review | Test Development | DLD Inspection | Code | Code Review | Compile | Code Inspection | Unit Test | Build and Integration Test | System Test | Documentation | Postmortem | Baseline Plan Date | Baseline Plan Hours

## Task
TSPi Task Planning Template - Form TASK | [13 empty] | Total Plan Hours | [6 empty] | Total Actual Hours
Name | Catálogo de Productos de Belleza Be Beautiful | [12 empty] | 93.1 | [6 empty] | 97.5
Team | Subgrupo 4 | [9 empty] | Reminder:
Date | 2026-06-23 | [9 empty] | If Size and Rate are present, estimated hours is calculated as Size / Rate
Instructor | Martinez, Natalia | [9 empty] | whenever the plan is updated. To prevent calculation, size or rate must be blank.
Cycle | Entrega 3 |  | Plan Hours by Role
Assembly | Phase | Task | Team Leader | Development Manager | Planning Manager | Quality/Process Manager | Support Manager | Developer / Tester de apoyo | Total Resource Hours | Resources | Estimated Size | Size Measure | Rate (per Hr.) | Time in Phase % | Estimated Hours | Engrs | Plan Hours | Plan Date | Plan Week | Actual Hours | Actual Date | Actual Week | Earned Value | Cumulative EV | Cumulative Plan Hours | Cumulative Plan Value | Plan Value | Predicted Date | Plan Date + Current Slip | Committed Date | Baseline Date | Baseline Plan Hours | Notes | Start Week | PHISW | PHIEW
Be Beautiful | DOC | T01 - Correcciones de Entrega 1 y ajustes del nombre Be Beautiful | 5 | 0 | 0 | 0 | 0 |  | 5 | Andrea | 36 | LOC proxy |  | 5.371% |  | 1 | 5 | 2026-05-27 | Semana 4 | 5.4 | 2026-05-27 | Semana 4 | 5 | 5 | 5 | 5 | 5 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 2026-05-27 | 5 | Ajustes de documento y normalización del proyecto. | Semana 4
Be Beautiful | MGMT | T02 - Repositorio, estructura de carpetas y ambiente local | 0 | 0 | 0 | 0 | 2 |  | 2 | Ángel | 20 | LOC proxy |  | 2.148% |  | 1 | 2 | 2026-05-28 | Semana 4 | 2.4 | 2026-05-28 | Semana 4 | 2 | 7 | 7 | 7 | 2 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2026-05-28 | 2 | Organización de soporte y evidencias. | Semana 4
Be Beautiful | CODE | T03 - Módulo de autenticación: registro, login y sesión local | 0 | 3.5 | 3.5 | 0 | 0 |  | 7 | Edison / Camilo | 64 | LOC proxy |  | 7.519% |  | 2 | 7 | 2026-06-02 | Semana 4 | 7.4 | 2026-06-02 | Semana 4 | 7 | 14 | 14 | 14 | 7 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 7 | Base para autenticación simulada. | Semana 4
Be Beautiful | CODE | T04 - Catálogo seed de 20 productos | 0 | 0 | 3 | 0 | 1 |  | 4 | Edison / Miguel | 96 | LOC proxy |  | 4.296% |  | 2 | 4 | 2026-06-03 | Semana 5 | 4.2 | 2026-06-03 | Semana 5 | 4 | 18 | 18 | 18 | 4 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 4 | Estructura local o mock de productos. | Semana 5
Be Beautiful | HLD | T05 - Interfaz de catálogo, tarjetas y filtros visuales | 3 | 4 | 0 | 0 | 0 |  | 7 | Andrea / Camilo | 65 | LOC proxy |  | 7.519% |  | 2 | 7 | 2026-06-03 | Semana 5 | 7.2 | 2026-06-03 | Semana 5 | 7 | 25 | 25 | 25 | 7 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 2026-06-03 | 7 | Avance visual del catálogo y filtros. | Semana 5
Be Beautiful | CODE | T06 - Vista de detalle de producto | 0 | 3.5 | 0 | 0 | 0 |  | 3.5 | Camilo | 16 | LOC proxy |  | 3.759% |  | 1 | 3.5 | 2026-06-04 | Semana 5 | 3.6 | 2026-06-04 | Semana 5 | 3.5 | 28.5 | 28.5 | 28.5 | 3.5 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 3.5 | Detalle de producto en construcción. | Semana 5
Be Beautiful | CODE | T07 - Búsqueda básica y búsqueda avanzada | 0 | 5 | 0 | 0 | 3 |  | 8 | Camilo / Miguel | 116 | LOC proxy |  | 8.593% |  | 2 | 8 | 2026-06-04 | Semana 5 | 8.4 | 2026-06-04 | Semana 5 | 8 | 36.5 | 36.5 | 36.5 | 8 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 2026-06-04 | 8 | Servicio de productos y filtros en integración. | Semana 5
Be Beautiful | CODE | T08 - Carrito de compras: agregar, actualizar y eliminar productos | 0 | 5 | 3 | 0 | 0 |  | 8 | Camilo / Edison | 93 | LOC proxy |  | 8.593% |  | 2 | 8 | 2026-06-05 | Semana 5 | 8.4 | 2026-06-05 | Semana 5 | 8 | 44.5 | 44.5 | 44.5 | 8 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 8 | Lógica simulada del carrito y reglas pendientes. | Semana 5
Be Beautiful | CODE | T09 - Validación de stock, subtotales y total general | 0 | 2.5 | 3 | 0 | 0 |  | 5.5 | Edison / Camilo | 45 | LOC proxy |  | 5.908% |  | 2 | 5.5 | 2026-06-05 | Semana 5 | 5.7 | 2026-06-05 | Semana 5 | 5.5 | 50 | 50 | 50 | 5.5 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 5.5 | Reglas de negocio preparadas. | Semana 5
Be Beautiful | CODE | T10 - Confirmación simulada de pedido | 1 | 0 | 0 | 0 | 1.5 |  | 2.5 | Andrea / Miguel | 12 | LOC proxy |  | 2.685% |  | 2 | 2.5 | 2026-06-06 | Semana 5 | 2.3 | 2026-06-06 | Semana 5 | 2.5 | 52.5 | 52.5 | 52.5 | 2.5 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2.5 | Cierre del flujo como componente planeado. | Semana 5
Be Beautiful | DOC | T11 - Mensajes del sistema y textos de interfaz | 1 | 0 | 0 | 1.5 | 0 |  | 2.5 | Cindy / Andrea | 40 | LOC proxy |  | 2.685% |  | 2 | 2.5 | 2026-06-06 | Semana 5 | 2.7 | 2026-06-06 | Semana 5 | 2.5 | 55 | 55 | 55 | 2.5 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2.5 | Revisión de textos y mensajes. | Semana 5
Be Beautiful | STP | T12 - Matriz de pruebas y ejecución funcional | 0 | 0 | 0 | 6 | 3 |  | 9 | Cindy / Miguel | 85 | LOC proxy |  | 9.667% |  | 2 | 9 | 2026-06-07 | Semana 5 | 9.5 | 2026-06-07 | Semana 5 | 9 | 64 | 64 | 64 | 9 | 2026-06-07 | 2026-06-07 | 2026-06-07 | 2026-06-07 | 9 | Casos de prueba diseñados/preparados. | Semana 5
Be Beautiful | IT | T13 - Corrección de defectos e integración del prototipo | 1 | 3 | 1 | 1.5 | 1 |  | 7.5 | Todo el equipo | 66 | LOC proxy |  | 8.056% |  | 5 | 7.5 | 2026-06-08 | Semana 5 | 8.2 | 2026-06-08 | Semana 5 | 7.5 | 71.5 | 71.5 | 71.5 | 7.5 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 7.5 | Corrección de defectos y revisión de integración. | Semana 5
Be Beautiful | PLAN | T14 - Workbook TSP, LOGT, LOGD, SUMS y reportes semanales | 0 | 0 | 9.5 | 0 | 0 |  | 9.5 | Edison | 146 | LOC proxy |  | 10.2% |  | 1 | 9.5 | 2026-06-08 | Semana 5 | 9.7 | 2026-06-08 | Semana 5 | 9.5 | 81 | 81 | 81 | 9.5 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 9.5 | Actualización de registros y métricas. | Semana 5
Be Beautiful | DOC | T15 - Actas, plan de calidad, riesgos y consolidado documental | 4.2 | 0 | 0 | 5.3 | 0 |  | 9.5 | Andrea / Cindy / equipo | 171 | LOC proxy |  | 10.2% |  | 2 | 9.5 | 2026-06-23 | Semana 5 | 10 | 2026-06-23 | Semana 5 | 9.5 | 90.5 | 90.5 | 90.5 | 9.5 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 9.5 | Consolidado documental de la entrega. | Semana 5
Be Beautiful | MGMT | T16 - Evidencias, respaldo, repositorio y soporte de entrega | 0 | 0 | 0 | 0 | 2.6 |  | 2.6 | Ángel / Miguel | 20 | LOC proxy |  | 2.793% |  | 1 | 2.6 | 2026-06-23 | Semana 5 | 2.4 | 2026-06-23 | Semana 5 | 2.6 | 93.1 | 93.1 | 93.1 | 2.6 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2.6 | Soporte final de evidencias. | Semana 5

## Schedule
TSPi Schedule Planning Template - Form SCHEDULE
| Name | Catálogo de Productos de Belleza Be Beautiful
| Team | Subgrupo 4 |  |  |  |  | Total Task Plan Hours | 93.1
| Date | 2026-06-23 |  |  |  |  | Total Schedule Plan Hours | 93.1
| Instructor | Martinez, Natalia |  |  |  |  | Difference | 0
| Cycle | Entrega 3
Date | Week | Planned Hours | Cumulative Planned Hours | Actual Hours | Cumulative Actual Hours | Planned Value | Cumulative Planned Value | Earned Value | Cumulative EV | Predicted Hours | Cumulative Predicted Hours | Predicted Earned Value | Cumulative Predicted Earned Value | Baseline Plan Hours | Baseline Cumulative Plan Hours | Baseline Plan Value | Baseline Cumulative Plan Value | Notes
2026-05-19 | Semana 2 | 14.5 | 14.5 | 15.2 | 15.2 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | Planeación inicial y organización del equipo.
2026-05-26 | Semana 3 | 22.7 | 37.2 | 23.7 | 38.9 | 22.7 | 37.2 | 22.7 | 37.2 | 22.7 | 37.2 | 22.7 | 37.2 | 22.7 | 37.2 | 22.7 | 37.2 | Cierre de Entrega 1 y preparación de mejoras.
2026-06-02 | Semana 4 | 26.9 | 64.1 | 28.4 | 67.3 | 25.6 | 62.8 | 25.6 | 62.8 | 26.9 | 64.1 | 25.6 | 62.8 | 26.9 | 64.1 | 25.6 | 62.8 | Actas 3 y 4, estimación por proxies, plan general.
2026-06-23 | Semana final / Entrega 3 | 29 | 93.1 | 30.2 | 97.5 | 27.8 | 90.6 | 27.8 | 90.6 | 29 | 93.1 | 27.8 | 90.6 | 29 | 93.1 | 27.8 | 90.6 | Calidad, riesgos, Workbook, evidencias y cierre documental.

## Risk
Risk | Impact | Likelihood | Priority | Assigned | Date
Disponibilidad limitada de integrantes | 5 | 3 | 15 | Team Leader | 2026-06-05
Inconsistencia entre nombres, categorías y documentos | 3 | 3 | 9 | Team Leader | 2026-06-05
Retraso en integración del carrito con stock | 5 | 3 | 15 | Development Manager | 2026-06-05
Búsqueda avanzada con resultados incorrectos | 4 | 4 | 16 | Quality Manager | 2026-06-05
Registro incompleto de tiempos en LOGT | 4 | 3 | 12 | Planning Manager | 2026-06-05
Defectos críticos abiertos cerca de la entrega | 5 | 2 | 10 | Quality Manager | 2026-06-05
Pérdida de archivos o versiones | 5 | 2 | 10 | Support Manager | 2026-06-05
Diseño visual consume más tiempo que funcionalidad | 3 | 3 | 9 | Development Manager | 2026-06-05
Falta de evidencia para sustentar avances | 4 | 2 | 8 | Support Manager | 2026-06-05
Cambios de alcance solicitados tarde | 4 | 2 | 8 | Team Leader | 2026-06-05

## LOGT
TSPi Time Recording Log - Form LOGT
Name | Catálogo de Productos de Belleza Be Beautiful |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  | Instructor | Martinez, Natalia
|  |  |  | Cycle | Entrega 3
|  |  |  | Hours | 97.5
Assembly | Phase | Task | Date | Start | Int. | Stop | Delta | Comments
Be Beautiful | PLAN | Andrea - Semana 2: acuerdos iniciales, roles y apoyo documental | 2026-05-19 |  | 0 |  | 2 | Planeación inicial y organización del equipo.
Be Beautiful | PLAN | Camilo - Semana 2: revisión técnica del alcance y estructura inicial | 2026-05-19 |  | 0 |  | 3.5 | Revisión del prototipo base y componentes técnicos.
Be Beautiful | PLAN | Edison - Semana 2: planificación, tareas y base del Workbook | 2026-05-19 |  | 0 |  | 4 | Organización inicial de tareas, responsables, tiempos y estructura del Workbook.
Be Beautiful | PLAN | Cindy - Semana 2: revisión de calidad inicial y criterios | 2026-05-19 |  | 0 |  | 2 | Apoyo en criterios de revisión.
Be Beautiful | MGMT | Ángel - Semana 2: apoyo de repositorio y evidencias iniciales | 2026-05-19 |  | 0 |  | 2.2 | Organización inicial de soporte.
Be Beautiful | MGMT | Miguel - Semana 2: apoyo en revisión del catálogo y evidencias | 2026-05-19 |  | 0 |  | 1.5 | Apoyo de revisión y soporte documental.
Be Beautiful | DOC | Andrea - Semana 3: cierre de Entrega 1 y revisión documental | 2026-05-26 |  | 0 |  | 2.5 | Revisión de documento y compromisos de mejora.
Be Beautiful | CODE | Camilo - Semana 3: ajustes técnicos iniciales del catálogo | 2026-05-26 |  | 0 |  | 9 | Base visual y componentes iniciales del prototipo.
Be Beautiful | PLAN | Edison - Semana 3: cierre de avance y preparación de la siguiente fase | 2026-05-26 |  | 0 |  | 5.5 | Ajustes de planeación y trazabilidad.
Be Beautiful | STP | Cindy - Semana 3: revisión de calidad del documento inicial | 2026-05-26 |  | 0 |  | 4.5 | Identificación de mejoras para la siguiente fase.
Be Beautiful | MGMT | Ángel - Semana 3: soporte de archivos y repositorio | 2026-05-26 |  | 0 |  | 1 | Organización de archivos base.
Be Beautiful | MGMT | Miguel - Semana 3: apoyo en revisión de componentes y evidencias | 2026-05-26 |  | 0 |  | 1.2 | Apoyo documental y técnico inicial.
Be Beautiful | DOC | Andrea - Semana 4: Acta 3, diseño conceptual y revisión de informe | 2026-06-02 |  | 0 |  | 3 | Ajuste de actas, texto y componentes del catálogo.
Be Beautiful | CODE | Camilo - Semana 4: arquitectura, búsqueda, detalle y carrito inicial | 2026-06-02 |  | 0 |  | 10.5 | Avance de estructura técnica e integración parcial.
Be Beautiful | PLAN | Edison - Semana 4: estimación por componentes, recursos, TASK y Schedule | 2026-06-02 |  | 0 |  | 7 | Estimación de tamaño, horas, recursos y seguimiento del proyecto.
Be Beautiful | STP | Cindy - Semana 4: matriz de pruebas y control de defectos | 2026-06-02 |  | 0 |  | 5 | Preparación de pruebas y revisión de calidad.
Be Beautiful | MGMT | Ángel - Semana 4: soporte de repositorio y evidencias | 2026-06-02 |  | 0 |  | 0.8 | Soporte técnico y organización de evidencias.
Be Beautiful | MGMT | Miguel - Semana 4: apoyo a catálogo, búsqueda y pruebas | 2026-06-02 |  | 0 |  | 2.1 | Apoyo en revisión de componentes.
Be Beautiful | DOC | Andrea - Semana final: consolidado final del informe, actas y sustentación | 2026-06-23 |  | 0 |  | 2.7 | Cierre documental de la Entrega 3 y revisión de coherencia final.
Be Beautiful | IT | Camilo - Semana final: integración final y revisión técnica del prototipo | 2026-06-23 |  | 0 |  | 11.7 | Revisión de carrito, búsqueda, estructura JavaScript y preparación de demo.
Be Beautiful | PLAN | Edison - Semana final: actualización del Workbook y cierre de planeación | 2026-06-23 |  | 0 |  | 7.5 | Consolidado de métricas finales, horas, fechas, desviación y trazabilidad de la entrega.
Be Beautiful | STP | Cindy - Semana final: calidad, LOGD, pruebas y riesgos de cierre | 2026-06-23 |  | 0 |  | 6.3 | Revisión de defectos, pruebas funcionales y riesgos antes del cierre.
Be Beautiful | MGMT | Ángel - Semana final: respaldo final, evidencias y paquete de entrega | 2026-06-23 |  | 0 |  | 0.8 | Soporte final de archivos, evidencias, respaldo y paquete de entrega.
Be Beautiful | MGMT | Miguel - Semana final: apoyo en pruebas, revisión funcional y cierre de evidencias | 2026-06-23 |  | 0 |  | 1.2 | Apoyo en pruebas funcionales, revisión de uso y evidencias para sustentación.

## LOGD
TSPi Defect Recording Log - Form LOGD
Name | Catálogo de Productos de Belleza Be Beautiful |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  | Instructor | Martinez, Natalia
|  |  |  | Cycle | Entrega 3
Date | Num | Type | Assembly | Injected | Removed | Fix Time | Fix Ref. | Description
2026-05-27 | 1 | 10 | Informe de avance | DOC | DOC | 0.4 | D-01 | Inconsistencia en el nombre del proyecto y referencias anteriores.
2026-05-27 | 2 | 40 | Roles | PLAN | DOC | 0.3 | D-02 | Miguel no aparecía de forma consistente en equipo, roles y evidencias.
2026-05-28 | 3 | 10 | Acta 3 | REQ | DOC | 0.4 | D-03 | Uso de términos como base de datos/backend sin implementación real.
2026-05-28 | 4 | 10 | Acta 3 | REQ | DOC | 0.2 | D-04 | Redacción sobre encriptación de contraseñas no correspondía al prototipo.
2026-05-29 | 5 | 70 | Catálogo | REQ | CODE | 0.5 | D-05 | Categorías del catálogo requerían normalización con el alcance definido.
2026-05-30 | 6 | 60 | Acta 4 | PLAN | PLAN | 0.6 | D-06 | Estimación inicial tenía demasiados ítems y se ajustó a 16 principales.
2026-05-30 | 7 | 60 | Acta 4 | PLAN | PLAN | 0.4 | D-07 | Horas y fechas no estaban alineadas con semanas académicas.
2026-06-01 | 8 | 70 | Workbook | PLAN | PLAN | 0.5 | D-08 | Inconsistencias entre LOC proxy, horas plan y consolidado del informe.
2026-06-02 | 9 | 80 | productService.js | CODE | CODE | 0.8 | D-09 | Servicio de productos requiere integración con datos locales o mock.
2026-06-03 | 10 | 80 | main.js | CODE | CODE | 0.7 | D-10 | Carrito solo aumenta contador, falta integración completa de cantidades.
2026-06-03 | 11 | 50 | Interfaz | CODE | CODE | 0.4 | D-11 | Botones de filtro tenían comportamiento visual sin conexión completa a datos.
2026-06-04 | 12 | 10 | Acta 6 | DOC | DOC | 0.3 | D-12 | Fechas de siguiente fase requerían ajuste para no contradecir entrega actual.
2026-06-05 | 13 | 10 | Acta 7 | DOC | DOC | 0.4 | D-13 | Título y fecha de gestión de riesgos necesitaban corrección.
2026-06-06 | 14 | 60 | LOGT/WEEK | PLAN | DOC | 0.6 | D-14 | Registros semanales incompletos antes de consolidar Punto 8.
2026-06-08 | 15 | 60 | Pruebas | STP | Pendiente | 0 | D-15 | Algunos casos de prueba quedan preparados, no ejecutados completamente.
2026-06-08 | 16 | 80 | Carrito | CODE | Pendiente | 0 | D-16 | Integración final de carrito, stock y totales queda para siguiente fase.

## Week
TSPi Week Summary - Form WEEK
Name | Catálogo de Productos de Belleza Be Beautiful |  |  |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  |  |  | Instructor | Martinez, Natalia
Status for Week | 5 | Selected Assembly |  |  |  | Cycle | Entrega 3
Week Date | 2026-06-23 | SYSTEM
Task Hours %Change |  | Weekly Data | Plan | Actual | Plan / Actual | Plan - Actual | Project End Date
Baseline | 0 | Schedule hours for this week | 29 | 30.2 | 0.96026 | -1.2 | Baseline | 2026-06-23
Current | 0 | Schedule hours this cycle to date | 93.1 | 97.5 | 0.95487 | -4.4 | Plan | 2026-06-23
%Change |  | Earned value for this week | 27.8 | 27.8 | 1 | 0 | Predicted
|  | Earned value this cycle to date | 90.6 | 90.6 | 1 | 0
|  | To-date hours for tasks completed | 93.1 | 97.5 | 0.95487
|  | To-date average hours per week | 23.275 | 24.375 | 0.95487
|  | EV per completed task hour to date | 0.97315 | 0.92923
|  | Consolidated Team Member Schedule Data |  | Plan Hours | Actual Hours | Plan Value | Earned Value
|  | Team Leader |  | 9.2 | 10.2 | 9.2 | 9.2
|  | Development Manager |  | 33.2 | 34.7 | 33.2 | 33.2
|  | Planning Manager |  | 23.2 | 24 | 23.2 | 23.2
|  | Quality/Process Manager |  | 16.8 | 17.8 | 16.8 | 16.8
|  | Support Manager |  | 10.7 | 10.8 | 10.7 | 10.7
Developer / Tester de apoyo
|  | Totals |  | 93.1 | 97.5 | 93.1 | 93.1
Development Tasks Completed | Phase | Task | Resource | Task Plan Hrs. | Task Actual Hrs. | Earned or Plan Value | Plan vs. Actual Hrs. | Baseline or Committed Date | Plan Date | Slip Date | Predicted Date | Actual Date
| DOC | T01 - Correcciones Entrega 1 | Andrea | 5 | 5.4 | 5 | 0.4 | 2026-05-27 | 2026-05-27 |  | 2026-05-27 | 2026-05-27
| MGMT | T02 - Repositorio y evidencias | Ángel | 2 | 2.4 | 2 | 0.4 | 2026-05-28 | 2026-05-28 |  | 2026-05-28 | 2026-05-28
| HLD | Acta 3 y diseño conceptual | Andrea / Camilo / Edison | 14 | 14.8 | 14 | 0.8 | 2026-06-02 | 2026-06-02 |  | 2026-06-02 | 2026-06-02
| PLAN | Acta 4 y estimación por proxies | Edison / Camilo | 9.5 | 9.7 | 9.5 | 0.2 | 2026-06-08 | 2026-06-08 |  | 2026-06-08 | 2026-06-08
| ST | Plan de calidad, riesgos y defectos | Cindy / Miguel | 20 | 21.1 | 20 | 1.1 | 2026-06-23 | 2026-06-23 |  | 2026-06-23 | 2026-06-23

## IRTL
TSPi Issue/Risk Tracking Log - Form IRTL
Name | Catálogo de Productos de Belleza Be Beautiful |  |  |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  |  |  | Instructor | Martinez, Natalia
[6 empty] | Cycle | Entrega 3
Issue or Risk Number | R=Risk I=Issue | Date Created | P=Personal T=Team | Likelihood (H,M,L) | Impact (H,M,L) | Owner | Follow-up Date | Description | Current Status | Date Status Changed
R-01 | R | 2026-06-05 | T | M | H | Team Leader | 2026-06-23 | Disponibilidad limitada de integrantes | Seguimiento alto | 2026-06-23
R-02 | R | 2026-06-05 | T | M | M | Team Leader | 2026-06-23 | Inconsistencia entre nombres, categorías y documentos | Mitigado / seguimiento | 2026-06-23
R-03 | R | 2026-06-05 | T | M | H | Development Manager | 2026-06-23 | Retraso en integración del carrito con stock | Seguimiento alto | 2026-06-23
R-04 | R | 2026-06-05 | T | H | H | Quality Manager | 2026-06-23 | Búsqueda avanzada con resultados incorrectos | Seguimiento alto | 2026-06-23
R-05 | R | 2026-06-05 | T | M | H | Planning Manager | 2026-06-23 | Registro incompleto de tiempos en LOGT | Mitigado / seguimiento | 2026-06-23
R-06 | R | 2026-06-05 | T | L | H | Quality Manager | 2026-06-23 | Defectos críticos abiertos cerca de la entrega | Mitigado / seguimiento | 2026-06-23
R-07 | R | 2026-06-05 | T | L | H | Support Manager | 2026-06-23 | Pérdida de archivos o versiones | Mitigado / seguimiento | 2026-06-23
R-08 | R | 2026-06-05 | T | M | M | Development Manager | 2026-06-23 | Diseño visual consume más tiempo que funcionalidad | Mitigado / seguimiento | 2026-06-23
R-09 | R | 2026-06-05 | T | L | H | Support Manager | 2026-06-23 | Falta de evidencia para sustentar avances | Mitigado / seguimiento | 2026-06-23
R-10 | R | 2026-06-05 | T | L | H | Team Leader | 2026-06-23 | Cambios de alcance solicitados tarde | Mitigado / seguimiento | 2026-06-23

## IRWeek
TSPi Issue Risk Week Summary - Form IRWEEK
Name | Catálogo de Productos de Belleza Be Beautiful |  |  |  | Date | 2026-06-23
Team | Subgrupo 4 |  |  |  | Team | Martinez, Natalia
Week | 1 | 5 |  |  | Cycle | Entrega 3
Issue/Risk Number | P=Personal T=Team |  | R=Risk I=Issue | Description |  | Status
R-01 | T |  | R | Disponibilidad limitada de integrantes |  | Seguimiento
R-02 | T |  | R | Inconsistencia entre nombres, categorías y documentos |  | Controlado
R-03 | T |  | R | Retraso en integración del carrito con stock |  | Seguimiento
R-04 | T |  | R | Búsqueda avanzada con resultados incorrectos |  | Seguimiento
R-05 | T |  | R | Registro incompleto de tiempos en LOGT |  | Controlado
R-06 | T |  | R | Defectos críticos abiertos cerca de la entrega |  | Controlado

## DefectTypes
Type | Description
10 | Documentation
20 | Syntax
30 | Build, Package
40 | Assignment
50 | Interface
60 | Checking
70 | Data
80 | Function
90 | System
100 | Environment

## Phases
Phase | Description | Task Generator S-System P-Part N-None | LOGT Track Time | LOGD Track Defects Injected | LOGD Track Defects Removed | PDF | DefDen | DefRatios | DevTimeRatio | RvwRate | PhaseYld | ProcYld | DI Rate | DR Rate
MGMT | Management and Miscellaneous | S | Y | N | N | N | N |  |  | N | N | N | N | N
STRAT | Launch and Strategy | S | Y | N | N | N | N |  |  | N | N | N | N | N
PLAN | Planning | S | Y | Y | Y | N | N |  |  | N | Y | Y | Y | Y
REQ | Requirements | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
STP | System Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
REQINSP | REQ Inspection | S | Y | Y | Y | N | Y |  | Requirements | Y | Y | N | Y | Y
HLD | High-Level Design | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
ITP | Integration Test Plan | S | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
HLDINSP | HLD Inspection | S | Y | Y | Y | N | Y |  | High-Level Design | Y | Y | N | Y | Y
DLD | Detailed Design | P | Y | Y | Y | N | N |  | Code | N | Y | N | Y | Y
DLDR | DLD Review | P | Y | Y | Y | N | Y | Unit Test | Detailed Design | Y | Y | N | Y | Y
TD | Test Development | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
DLDINSP | DLD Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
CODE | Code | P | Y | Y | Y | N | N |  |  | N | Y | N | Y | Y
CR | Code Review | P | Y | Y | Y | N | Y | Compile | Code | Y | Y | N | Y | Y
COMPILE | Compile | P | Y | Y | Y | y | Y |  |  | N | Y | Y | Y | Y
CODEINSP | Code Inspection | P | Y | Y | Y | N | Y |  |  | Y | Y | N | Y | Y
UT | Unit Test | P | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
IT | Build and Integration Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
ST | System Test | S | Y | Y | Y | Y | Y |  |  | N | Y | Y | Y | Y
DOC | Documentation | S | Y | N | N | N | N |  |  | N | N | N | N | N
PM | Postmortem | S | Y | N | N | N | N |  |  | N | N | N | N | N
AT | Acceptance Test | N | N | Y | Y | Y | Y |  |  | N | N | Y | N | N
PL | Product Life | N | N | Y | Y | Y | Y |  |  | N | N | N | N | N

## QProfParam
Parameter | Value | Description
Design/Code Time | 100% | Design time as % of coding time
Code Review Time | 50% | Code review time as % of code time
Compile Defects/KLOC | 10 | Compile defects/KLOC
Unit Test Ddefects/KLOC | 5 | Unit test defects/KLOC
Design Review Time | 50% | Design review time as % of design time

## Roles_E3
Roles TSP, aportes reales y manejo autodirigido del equipo
Integrante | Rol formal TSP | Responsabilidad esperada | Aporte real observado | Evidencia | Horas plan | Horas real | Análisis para defender
Andrea Lozano Beltrán | Team Leader | Coordinar reuniones, compromisos, alcance y comunicación. | Coordinó acuerdos, actas, revisión documental, textos de interfaz y preparación de sustentación. | Actas, informe y consolidado documental. | 9.2 | 10.2 | Mantuvo el enfoque en la rúbrica y ayudó a que el equipo no dejara evidencias para el final.
Camilo Mesa Molina | Development Manager | Guiar el desarrollo técnico y la integración del producto. | Lideró interfaz, búsqueda, detalle, carrito, reglas de stock y corrección de defectos funcionales. | Módulos JS y pruebas funcionales. | 33.2 | 34.7 | Convirtió el catálogo en prototipo funcional y no solamente visual.
Edison Norvey Luis Sánchez | Planning Manager | Gestionar plan, tareas, tiempos, métricas, cronograma y desviaciones del proyecto. | Organizó el plan de trabajo, actualizó TASK, Schedule, LOGT y métricas; además apoyó la arquitectura, validaciones, pruebas manuales y revisión de lógica cuando el equipo lo necesitó. | Workbook TSP, TASK, Schedule, LOGT, SUMS, métricas LOC y pruebas manuales. | 23.2 | 24 | Su responsabilidad principal fue dejar clara la planeación y el seguimiento; el apoyo técnico quedó como colaboración propia de un equipo autodirigido.
Cindy Lugo Polo | Quality/Process Manager | Controlar proceso, calidad, riesgos, defectos y consistencia. | Revisó defectos, riesgos, coherencia del informe, pruebas manuales y diferencias entre lo documentado y lo implementado. | LOGD, Risk, informe final y pruebas. | 16.8 | 17.8 | Ayudó a evitar afirmaciones técnicas no implementadas y a priorizar defectos relevantes para sustentación.
Ángel Damian Jiménez Betancourt | Support Manager | Asegurar repositorio, respaldo, estructura y evidencias. | Organizó archivos, respaldos, soporte de entrega y disponibilidad del paquete final. | ZIP, carpeta de evidencias y paquete final. | 3.7 | 4.8 | Su rol redujo riesgo de pérdida de versiones y mejoró la reproducibilidad.
Miguel Montañez Ruiz | Developer/Tester de apoyo | Apoyar desarrollo, pruebas y revisión funcional. | Se incorporó en segunda fase; reforzó pruebas manuales, revisión de búsqueda, perspectiva de usuario y cierre de evidencias. | Actas, pruebas y cierre funcional. | 7 | 6 | Su ingreso funcionó como relanzamiento interno y ayudó a equilibrar carga.

## Pruebas_E3
Pruebas funcionales finales del catálogo Be Beautiful
ID | Módulo | Escenario | Procedimiento manual | Resultado esperado | Resultado obtenido | Estado | Evidencia | Criterio de rúbrica
P01 | Artículos | Validar 20 productos | Abrir catálogo y contar productos cargados. | 20 artículos visibles o disponibles en datos. | 20 productos encontrados. | PASS | products.js | Módulo artículos
P02 | Artículos | IDs únicos | Revisar identificadores del arreglo de productos. | No debe haber IDs repetidos. | IDs únicos. | PASS | products.js | Módulo artículos
P03 | Artículos | Campos completos | Revisar nombre, precio, categoría, stock e imagen. | Todos los campos requeridos completos. | Campos completos. | PASS | products.js | Módulo artículos
P04 | Artículos | Características visibles | Abrir detalle o revisar features por producto. | Cada producto debe tener características. | Características disponibles. | PASS | features | Módulo artículos
P05 | Disponibilidad | Producto agotado | Filtrar o revisar productos sin stock. | Debe existir al menos un producto agotado. | B020 con stock 0. | PASS | products.js | Stock
P06 | Búsqueda básica | Buscar con tilde | Buscar sérum. | Debe retornar resultados relacionados. | Retorna resultados. | PASS | productService.js | Búsqueda básica
P07 | Búsqueda básica | Buscar sin tilde | Buscar serum. | Debe retornar resultados aunque no tenga tilde. | Retorna resultados. | PASS | productService.js | Búsqueda básica
P08 | Búsqueda avanzada | Filtro combinado | Aplicar categoría, precio y disponibilidad. | Solo productos que cumplan criterios. | Retorna resultados válidos. | PASS | productService.js | Búsqueda avanzada
P09 | Registro | Usuario válido | Registrar usuario nuevo. | Registro exitoso. | Crea usuario local. | PASS | authService.js | Registro
P10 | Registro | Correo duplicado | Registrar dos veces el mismo correo. | Debe rechazar duplicado. | Rechaza repetidos. | PASS | authService.js | Registro
P11 | Inicio de sesión | Login correcto | Ingresar correo y contraseña válidos. | Sesión activa. | Inicia sesión local. | PASS | authService.js | Registro
P12 | Carrito | Agregar producto | Agregar artículo desde catálogo/detalle. | Producto aparece en carrito. | Agrega artículo. | PASS | cartService.js | Carro de compras
P13 | Carrito | Subtotal y total | Agregar cantidades y revisar total. | Total = precio x cantidad. | Calcula total. | PASS | cartService.js | Carro / compra
P14 | Stock | Límite de stock | Aumentar cantidad por encima del stock. | No debe permitir superar stock. | Respeta límite. | PASS | cartService.js | Compra / stock